## 1
TEAM 2 C1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Therese Mary Nshimyumurwa | Team Lead | t.nshimyumu@alustudent.com
Aimable Bancunguye | Backend and Database | a.bangunguy@alustudent.com
Eloi Mizero | ETL and Testing | e.mizero@alustudent.com
Davy Dushimiyimana | Frontend and Integration | d.dushimiyi@alustudent.com
Clive Tanaka Mushipe | Documentation and QA | c.mushipe@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Create Team Task sheet | Clive Tanaka Mushipe | 2026-05-18 | Completed | Yes
| Create ERD Diagram | Davy Dushimiyimana | 2026-05-18 | Completed | Yes
| SQL Database Implementation | Therese Mary Nshimyumurwa | 2026-05-18 | Completed | Yes
| Database Demo fuctionality | Aimable Bancunguye | 2026-05-18 | Completed | Yes
| Database Design Document | Clive Tanaka Mushipe | 2026-05-18 | Completed | Yes
| Update scrum board | Eloi Mizero | 2026-05-18 | Completed | Yes
| Team Lead / API Development | Therese Mary Nshimyumurwa | 2026-05-29 | Completed | Yes
| DSA & Data Parsing | Aimable Bancunguye | 2026-05-29 | Completed | Yes
| Backend Support & Testing | Davy Dushimiyimana | 2026-05-29 | Completed | Yes
| Documentation & API Docs | Eloi Mizero | 2026-05-29 | Completed | Yes
| Data Parsing & XML Processing | Clive Tanaka Mushipe | 2026-05-29 | Completed | Yes
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-05-16 | Week 2 assignment plan | Clive Tanaka Mushipe | Therese Mary Nshimyumurwa, Aimable Bancunguye, Eloi Mizero, Davy Dushimiyimana, Clive Tanaka Mushipe | Assiged roles and agreed on an aproach. | Complete assiged tasks.
2026-05-18 | Final review, organization and submition | Clive Tanaka Mushipe | Therese Mary Nshimyumurwa, Aimable Bancunguye, Eloi Mizero, Davy Dushimiyimana, Clive Tanaka Mushipe | Task completion | Submit
2026-05-28 | Building and Securing a REST API planning | Clive Tanaka Mushipe | Therese Mary Nshimyumurwa, Aimable Bancunguye, Eloi Mizero, Davy Dushimiyimana, Clive Tanaka Mushipe | Assigning tasks | Complete assiged tasks.
2026-05-29 | Building and securing a REST api Final review, organization and submition | Clive Tanaka Mushipe | Therese Mary Nshimyumurwa, Aimable Bancunguye, Eloi Mizero, Davy Dushimiyimana, Clive Tanaka Mushipe | Task completion | Submit